## Document Control
(Forrestry Camera Project) Test Report - Review log
Revision History
Version | Date | Author | Description | Reviewed | Date
0.1 |  | MO | Added example test cases for first static unit and integration tests for format review | AB/PC | 2022-03-04
0.2 |  | MO | Added all relevant test cases for static, unit, dynamic and integration tests relating to the camera controller (raspberry pi)
0.3 |  | MO | Updated tests for C Code application and new Workswell camera
0.4 |  | MO | Updated after testing on 64 bit ManJaro Linux | AK | 2022-08-25
0.5 |  | MO | Updated after testing on 64 bit ManJaro Linux and x86 with ubuntu18 | AK | 2022-08-30
0.6 |  | MO | Updated after testing on 64 bit ManJaro Linux and x86 with ubuntu18 with kernel performance and powersave set-up | AK | 2022-09-02

## Static Tests
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Run By
1 |  |  | Static Code Check | Static code check with flake8 |  | install flake8 and plugins pip install flake8 flake8-import-order | installs without issue | as described to left | pass | MO |  | 1 | not applicable
3 | [5 empty] | run flake8 on all python code | check results for syntax error, library order, and other potential errors and correct, ignore spacing style errors | as described to left | pass | MO |  | 1 | not applicable
2 |  |  | Static Code Check | Static code check with lint |  | run py lint on all code | remove warnings | as described to left | pass | MO |  | 1 | not applicable
4 |  |  |  | check compiler warnings |  | remove relevant warnings shown by various compilers | only trivial or warnings pertaining to client libraries which do not have any possible detrimental effect persist |  | not applicable |  |  | 1 | pass | MO
5 |  |  |  | static code check with Cppcheck 2.8 |  | check with Cppcheck 2.8 | no issues persist that could be an issue |  | not applicable |  |  |  | not done yet
6 |  |  |  | static code check with klocwork |  | check with klockwork | no issues persist that could be an issue |  | not applicable |  |  |  | not done yet

## Unit Tests
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Comments | Run By
3 |  |  | Unit Test | Unit Test functionality to camera |  | write wrapper which returns data as if it was the camera and with a delay | each options parses the information correctly and processes errors as desired should replies be wrong or non exhistant | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Unit Test | Unit Test functionality of multi-tasking |  | use multi-process to run camera task and heartbeat concurrently | program functions quicker with heartbeat keeping 1hz frequency to prevent QGC timeout | program functions task wise correctly but no message sent to mavlink from multi-process | fail | MO | logged info with pymavlink, not sure of course and the solution has been attained another way | 1 | fail | tried boost multithreading works fine but doesn’t sent mavlink inside thread try boost asio stranding | MO
5 |  |  | Unit Test | Unit Test functionality of multi-tasking |  | use MPI to run camera task and heartbeat concurrently | program functions quicker with heartbeat keeping 1hz frequency to prevent QGC timeout | tasks and inter-rank communication works correctly but no message sent to mavlink from MPI | fail | MO | logged info with pymavlink, not sure of course and the solution has been attained another way | 1 | n/a
15 |  |  | Unit Test | perfrom camera action in state engine |  | initialte action | that each action completes without error in a queue and no failure occurs by triggering the strand too often and the program is free to perfrom other actiosn while the camera strand is waiting | that timing and so many states became messy to manage | n/a |  |  |  | intermiitant
16 |  |  | Unit Test | perform action using poco threading |  | initialte action | that each action completes without error in a queue and no failure occurs by triggering the strand too often and the program is free to perfrom other actiosn while the camera strand is waiting |  | n/a |  |  |  | partially tested | example made not integrated to camera in code yet or tested
14 |  |  | Unit Test | multi-starnding using boost |  | run each camera action from multi-starnding using boost | that each action completes without error in a queue and no failure occurs by triggering the strand too often and the program is free to perfrom other actiosn while the camera strand is waiting |  | n/a |  | program ready to test |  | partially tested
17 |  |  | Unit Test | use timer interrupt |  | initiate test code at interval of timer | initiates heartbeat at frequency of timer irrespoective of program flow |  | n/a |  |  |  | pass | can use linux or poco library to do this
6 |  |  | Unit Test | Unit Test functionality of multi-tasking |  | send heartbeat for standby when busy task running and increase QGC timeouts | no drop in communications to QGC during camera actions | as described to left | pass | MO | above method solves above issues to permit product release | 1 | pass | send program heartbeat via timed interrupt | MO
7 |  |  | Unit Test | Unit Test functionality of hardwired interrupt |  | set DIN state and take photo | immediately takes picture | as described to left | not implemented in python | MO |  | 1 | pass |  | MO
8 |  |  | Unit Test | Unit Test functionality ini config file |  | read .ini file with all settings | check they are correct with what was written in the file | as described to left | not implemented in python | MO |  | 1 | pass |  | MO
9 |  |  | Unit Test | Unit Test functionality of xml default |  | read .xml file for items with menu defaults | check they are correct with what was written in the file | as described to left | not implemented in python | MO |  | 1 | pass |  | MO
10 |  |  | Unit Test | Unit Test functionality of saved set-up |  | save and recall current set-up (periodically if change made and no activity for 5 seconds) | settings are saved and recalled correctly when requested to do so from ini file | as described to left | not implemented in python | MO |  | 1 | pass |  | MO
11 |  |  | Unit Test | Unit Test functionality of reading shutter speed from xml |  | read possible shutter speed values from xml | tag is found in xml and all values are loaded sequentially into a vector for further use in the code | as described to left | not implemented in python | MO |  | 1 | pass |  | MO
12 |  |  | Unit Test | Unit Test functionality of reading Herelink RawChanel messages |  | setting correct mode and shutter speed, gimbal, near/far focus | functionality sets the structure outputs according to the herelink actions | as described to left | not implemented in python |  |  | 1 | not tested
13 |  |  | Unit Test | Unit Test functionality of communicating with Gremsy gimbal |  | set gimbal positions using test code communicating on serial UART2 | movement of gimbal in directions as expected for each signal sent with test code | as described to left | not implemented in python |  |  | 1 | not tested
14 |  |  | Unit Test | Unit Test functionality of boost stranding |  | use random generator sequence to make multiple chamges to the camera and obsere if they queue and each is performed in series | action performed in series and doesn’t crash camera and usb doesn’t need reset | initially yes then stops (perhaps 2 seconds wait between actions is not enough) | fail | MO |  | 1 | fail |  | MO
15 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on raspberry pi 4 with manjaro linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO |  | 1 | fail |  | MO
16 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on raspberry pi 4 with rasbian linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO | logged error on github - initially thought that kernel upgrade fixed this error | 1 | fail |  | MO
17 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on x86 ubuntu 18 linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO | logged error as https://github.com/mavlink-router/mavlink-router/issues/374 | 1 | fail |  | MO
18 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on raspberry pi 4 with manjaro linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO | tried with cpulimit at 60% on both applications | 1 | fail |  | MO
19 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on raspberry pi 4 with rasbian linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO | tried with cpulimit at 60% on both applications | 1 | fail |  | MO
20 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on x86 ubuntu 18 linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | initially yes then stops error shows mavlink-routerd stopping due to poll error and top shows 100% load | fail | MO | tried with cpulimit at 60% on both applications | 1 | fail |  | MO
21 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | test mavlink application on raspberry pi 4 with manjaro linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | can only connect 1x Mission Planner when cpulimits set to 30% | fail | MO |  | 1 | fail |  | MO
22 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | Optimise kernel and powersave and performance cpu as per instructions test mavlink application on x86 ubuntu 18 linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | works very fast never misses camera trigger | pass | MO |  | 1 | pass |  | MO
23 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | Optimise kernel and powersave and performance cpu as per instructions then test mavlink application on raspberry pi 4 with manjaro linux with mission planner(x2) QGC(x1) connected | program timer interrupt functions without stopping and periodically sends message over mavlink | works but is missing the odd message trigger or it is delayed by 1-2 seconds | fail | MO |  | 1 | pass |  | MO
24 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | Repeat test 22 after a reboot | program timer interrupt functions without stopping and periodically sends message over mavlink | works very fast never misses camera trigger | pass | MO |  | 1 | pass |  | MO
25 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | Re-instate the interrupt to slow down unwanted mavlink stream messages and repeat test 22 after a reboot | program timer interrupt functions without stopping and periodically sends message over mavlink | works very fast never misses camera trigger | pass | MO |  | 1 | pass |  | MO
26 |  |  | Unit Test | Unit Test functionality of mavlink-routerd |  | Re-instate the interrupt to slow down unwanted mavlink stream messages and repeat test 22 after a reboot also activate picture take in camera using /home/mogimods/sony-sdk/build/RemoteCli | program timer interrupt functions without stopping and periodically sends message over mavlink camera continues to take pictures and aperture white balance etc can change without delay or error | works very fast never misses camera trigger | pass | MO |  | 1 | pass |  | MO

## xmlfile
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Run By
1 |  |  | options | menu is sent when network connection made to pi | 1 | connect to raspberry pi using Qgroundcontrol | menu appears from xml | as described to left | pass | MO/VJKRM |  | 1 | pass | MO/AD
2 |  |  | values | shows valid options | 2 | check value for each option and that all requested options are showing | shows valid options | as described to left | pass | MO/VJKRM |  | 1 | pass | MO/AD
3 |  |  | values | shows all options | 3 | traverse down list and see that all options required (from camera SDS) are showing | shows all options | as described to left | pass | MO/VJKRM |  | 1 | pass | MO/AD
4 |  |  | send | send value | 4 | click on a menu item for each category and send | shows all options | as described to left | pass | MO/VJKRM |  | 1 | sent | MO/AD | the data appeared wrong and program has been modified
5 |  |  | restart | flask http server keeps running | 5 | stop flask http server with kill -9 instruction | restarts | as described to left | pass | MO/VJKRM |  | 1 | pass | MO/AD
6 |  |  | file error | check that file exists | 6 | remove file and get message that file is not present | error message and exit |  | n/a |  |  | 1 | not tested / partial implementation | MO/AD
7 |  |  | menu text | locale | 7 | check that the menu text corresponds to that written in the xml file for your current locale | as per xml descriptions | as described to left | pass | MO/VJKRM |  | 1 | pass | MO/AD
8 |  |  | options | menu is sent when NO network connection made to pi via mavlink ftp | 1 | connect to raspberry pi using Qgroundcontrol | menu appears from xml | as described to left | n/a |  |  | 1 | not tested / partial implementation | MO/AD
9 |  |  | values | shows valid options | 2 | check value for each option and that all requested options are showing | shows valid options | as described to left | n/a |  |  | 1 | not tested / partial implementation | MO/AD
10 |  |  | values | shows all options | 3 | traverse down list and see that all options required (from camera SDS) are showing | shows all options | as described to left | n/a |  |  | 1 | not tested / partial implementation | MO/AD
11 |  |  | send | send value | 4 | click on a menu item for each category and send | shows all options | as described to left | n/a |  |  | 1 | not tested / partial implementation | MO/AD
12 |  |  | menu text | locale | 5 | check that the menu text corresponds to that written in the xml file for your current locale | as per xml descriptions | as described to left | n/a |  |  | 1 | n/a | MO/AD

## WorksWell Wiris Pro
Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No
Compile and set-up communicator for ethernet |  | load boost on pi and get example to compile | no error | worked for C++17 and made work for c++11 if needed | pass | MO |  | 1
Write libraries for all possible workswell ethernet commands below |  | compiled | no error |  | pass | MO |  | 1
activate SDK license |  | enter the key and re-compile code | activates SDK and communicates with camera |  | not tested |  | should the key be read from file ? | 1
Take photo |  | command to take photo from comamnd line |  | picture taken from camera | not tested |  | requires license | 1 | There is delay on no license
start record |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
recording finish |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
recording state |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
thermal shutter |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set to default |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
shutdown |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
reboot |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set emissivity |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set shutter speed |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set syn shutter |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set radio jpeg |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set radio tiff |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set super res |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set vis image |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set radio vid |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set visibile video |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set thermo range high |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set image location |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set range mode |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set manual range |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set span range |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set time |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set cold reject |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set thermal trans |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
zoom in |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
zoom index |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
menu move |  | initiate action described on the left |  | nove menus successfully in all manners | not tested |  | requires license | 1
set layout |  | initiate action described on the left |  | action executed successfully | not tested |  | requires license | 1
set camera mode |  | thermal or visible mode |  | swaps mode correctly and indicates correctly on GUI | not tested |  | requires license | 1
get capture status |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get record statatus |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get range and environment |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get hot/cold rejection |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get time stabilization |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get all temperatures |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get thermal/visible zooms |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get pallette |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get shuuter period and sync |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get emissivity |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get time to next thermal shut |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get image ratio for jpeg tiff super etc |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get video properties |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get memory status / free memory |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get image location |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get date & time |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get thermal/visible video record times |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
get thermal cam resoultion, exteemes & pallette |  | initiate read of state |  | value represents that in camera | not tested |  | requires license | 1
using a hardwired connection |  | Open then re-close digital input contact GPIO No. 4 on pi to initiate camera take photo pulses |  | picture is taken with no latency for every pulse | not tested |  | requires license | 1
using a hardwired connection |  | Wire Pi digital input signal GPIO No. 4 to FCU and initiate camera take photo pulses |  | picture is taken with no latency | not tested |  | requires license | 1
boost logger (performance) |  | monitor performance of operations using boost logger | best performance path is chosen upon results |  | not tested |  | requires license | 1
wifi conenction fail |  | reset connection by powering off workswell camera | camera continues to communicate after reconnection |  | not tested |  |  | 1
mavlink router |  | kill mavlink-router daemon | task respawns |  | pass | MO |  | 1
setings are read from ini file |  | read workswell section of ini file | data is shown as requested | as per left | pass | MO |  | 1

## MicaSense Take Photos
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No |  | re-test C Code | Run By
1 |  |  | Take a Picture | MicaSense RedEdge Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 |  | pass | MO
[6 empty] | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 |  | pass | MO
[6 empty] | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload | as described to left | pass |  |  | 1 |  | pass | MO
2 |  |  | Take a Picture | MicaSense RedEdge Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 |  | not tested yet
[6 empty] | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 |  | not tested yet
[6 empty] | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload | as described to left | pass | MO |  | 1 |  | not tested yet
3 |  |  | Take a Picture | MicaSense RedEdge Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 |  | pass | MO
[6 empty] | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 |  | pass | MO
[6 empty] | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload |  |  |  |  | 1 |  | pass | MO
4 |  |  | Take a Picture | MicaSense RedEdge Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 |  | not tested yet
[6 empty] | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 |  | not tested yet
[6 empty] | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload | as described to left | pass | MO |  | 1 |  | not tested yet
5 |  |  | Calibrate Camera | MicaSense RedEdge Camera Calibrate |  | Change command to issue calibrate through API then Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | not implemented as yet | not tested yet
[6 empty] | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 |  | not tested yet
[6 empty] | Move towards camera with calibration plate until opertion has returned completion (and repeat 3 times) | Operation completes with success returned from the camera | as described to left | pass | MO |  | 1 |  | not tested yet
|  |  |  | set exposure settings |  | Send Command to change exposure | Camera changes as per request | coded but ----> | not tested |  |  | 1 | coded but ---> | not tested
|  |  |  | get exposure settings |  | Send Command to get current exposure set-up | values are extracted from json message and displayed correctly |  | pass | MO |  | 1 |  | pass | MO
|  |  |  | using a hardwired connection |  | wire Pi digital input signal to GPIO No. 4 to FCU and initiate camera take photo pulses | picture is taken with no latency |  | not tested |  |  |  | coded but ----> | not tested
|  |  |  | boost logger (performance) |  | monitor performance of operations using boost logger | best performance path is chosen upon results |  | n/a |  |  |  | coded but ----> | not tested
|  |  |  | wifi conenction fail |  | reset connection by powering off micasense camera | camera continues to communicate after reconnection |  | pass | MO |  | 1 |  | not tested | MO
|  |  |  | mavlink router |  | kill mavlink-router daemon | task respawns |  | pass | MO |  | 1 |  | pass | MO
|  |  |  | setings are read from ini file |  | read micasense section of ini file | data is shown as requested | data is shown as requested | pass | MO |  | 1

## Sony Camera General
Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Run By | Comments
boost logger (performance) |  | monitor performance of operations using boost logger | best performance path is chosen upon results |  | not tested |  |  | 1 | not tested
Sony Alpha Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | MO
|  | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass | MO
|  | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload | as described to left | pass |  |  | 1 | pass | MO
Sony Alpha Camera Take Photo |  | Power up camera and connect to Raspberry Pi ensure wifi is enabled | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | MO/AD
|  | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass | MO/AD
|  | Send Command to take picture (repeat many times) | Camera takes picture whenever button is pressed with very little delay or latency and uploads to Pi if requested to do so otherwise no upload | as described to left | pass | MO |  | 1 | pass | MO/AD
using a hardwired connection |  | simulate digital input signal to GPIO No. 4 as if it was conencted to the FCU and initiate camera take photo pulses | picture is taken with no latency |  | not tested |  |  | 1 | pass | MO/AK
using a hardwired connection |  | wire Pi digital input signal to GPIO No. 4 to FCU and initiate camera take photo pulses | picture is taken with no latency |  | not tested |  |  | 1 | not tested
get disk space and free space |  | print the pi disk space free total and used | reports disk data to console |  | not tested |  |  | 1 | pass | MO
report get disk space and free space |  | look at GCS to see camera disk free and usage | pi sends message back to GCS for display of pi data as above |  | not tested |  |  | 1 | not tested | MO
start video recording |  | initialte start video from Mission Planner | video indicates as running from camera_status message and video has began recording |  | pass | MO |  | 1 | not tested | MO
stop video recording |  | stop video record from mission Planner | video recording stops |  | pass | MO |  | 1 | not tested | MO
start video recording |  | initialte start video from QGC | video indicates as running from camera_status message and video has began recording |  | pass | MO |  | 1 | not tested | MO
stop video recording |  | stop video record from QGC | video recording stops |  | pass | MO |  | 1 | not tested | MO
change parameters with MAVLINK_MSG_ID_DIGICAM_CONFIGURE |  | set-up camera | all parameters are written as expected to the camera |  | not tested | MO |  | 1 | not tested | MO
change parameters with MAV_CMD_DO_DIGICAM_CONFIGURE |  | set-up camera | all parameters are written as expected to the camera |  | not tested |  |  | 1 | not tested | MO
take photo using MAV_CMD_DO_DIGICAM_CONTROL |  | command this from the mission planner menu | takes a photo |  | pass | MO |  | 1 | not tested | MO
take photo using MAV_CMD_DO_DIGICAM_CONTROL |  | command this from the GCS | takes a photo |  | pass | MO |  | 1 | not tested | MO
take picture using MAVLINK_MSG_ID_DIGICAM_CONTROL |  | command this from the GCS | takes a photo |  | pass | MO |  | 1 | not tested | MO
check heartbeat |  | observe on GCS GUI | shows 1Hz consistant |  | pass/sometimes drops | MO | drops out and is told to back off during camera action could not get MPI or multi-thread to work | 1 | pass | MO/AD
gets correct ID from GCS |  | observe messages from mavlink in Mission Planner via set-up advanced -> Mavlink Inspector | shows ID as expected |  | pass | MO |  | 1 | not tested | MO
usb conenction fail |  | reset connection by pulling cable | camera continues to communicate |  | pass | MO |  | 1 | pass | MO | requires poco library and uhubctrl
mavlink router |  | kill mavlink-router daemon | task respawns |  | pass | MO |  | 1 | pass | MO
mavlink receive buffer overflow |  | create buffer overflow by requesting and sending messages at 100Hz or sending from numerous GCS | buffer is reset |  | pass | MO/VJKRM |  | 1 | not tested
gimbal serial receive buffer overflow |  | simulate high feedback message by sending fast messages to gimbal | ensure no effect on program or serial communication and gimbal speed is acceptable |  | not tested |  |  | 1 | not tested

## SonyCamera RawServo Change Val
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results(Web) | Pass/Fail | Run By | Comments | Issue No |  | re-test C Code | Run By
1 | 1 |  | change mode |  | 1 | with herelink use the method described in FDS spreadsheet to change to operation to each mode | the mode switches between each respective mode listed in the enum in the spreadsheet - status message sent |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
2 | 2 |  | gimbal mode |  | 3 | gimbal is connected on serial UART2 to raspberry pi and set to gimbal mode using raw servo message | gimbal is controlled from herelink as expected when set to be in the gimbal mode - status message sent |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
3 | 3 |  | shutter speed mode |  | 1 | set to shutter speed mode using herelink then use the control to move the shutter speed up/down | the shutter speed can be seen to move up and down the scale until it reaches either end stop then reset - status message sent |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
4 | 4 |  | near/far focus mode |  | 1 | set to shutter speed mode using herelink then use the control to move the focus near/far | the focus near/far setting can be seen to move up and down the scale with the value of the raw channel analogue until it reaches the end it then stops until the analogue value rises again - status message sent |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
5 | 5 |  | aperture mode |  | 1 | set to aperture mode using herelink | a message apears and NO further action is made |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
6 | 6 |  | iso mode |  | 1 | set to iso mode using herelink | a message apears and NO further action is made |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
| 7 |  | default settings |  | 1 | check that on start-up the default settings specified in the ini file have been read for the channels and start values | all values print as per the ini file and that matches the FDS spreadsheet |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
| 8 |  | default settings |  | 1 | check that on start-up if the ini file specifies xml that the shutter speed default setting comes from there instead with the other from the .ini file | all values print as per the ini file and xml and that matches the FDS spreadsheet |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
| 9 |  | last known values |  | 1 | program starts with last known values if requested by xml | shuter speed and near/far remain or go to the last used settings |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet
| 10 |  | change value |  | 1 | change value of shutter speed from parameter page of GCS | ensure shutter speed control on herelink now increments decrements from the new setting written |  | not implemented in python |  |  | 1 | programmed but …> | not tested yet

## Sony Camera Change Aperture
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results(Web) | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the aperture to each of the following values 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the aperture to each of the following values 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the aperture to each of the following values 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the aperture to each of the following values 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for aperture and observe camera | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD
[5 empty] | 5 | observe menu indicator shows correct aperture setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR | with modified qgc | 2 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2 | pass |  | MO
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2 | pass |  | MO
[5 empty] | 4 | select each option for aperture and observe camera | camera changes the aperture to F2.8 F3.2 etc as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2 | pass |  | MO
[5 empty] | 5 | observe menu indicator shows correct aperture setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2 | pass |  | MO
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the aperture to each of the following values 250: 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes to requested setting | as described to left | pass | MO | using 64bit manjaro o/s and works fine but we see same reset phenomina as always | 1 | pass |  | MO
6 |  |  | Change Aperture setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the aperture to each of the following values 250: 280: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Change ISO
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the iso to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: | camera changes the iso as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the iso to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: | camera changes the iso as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the ISO to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: | camera changes the ISO as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the ISO to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: | camera changes the ISO as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for iso and observe camera | camera changes the iso as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for iso and observe camera | camera changes the iso as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the aperture to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO
6 |  |  | Change ISO setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu 18 x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the aperture to each of the following values 0: 50: 64: 80: 100: 125: 160: 200: 250: 320: 400: 500: 640: 1000: 1250: 1600: 2000: 2500: 3200: 4000: 5000: 6400: 8000: 10000: 12800: 16000: 20000: 25600: 32000: 40000: 51200: 64000: 80000: 102400: 320: 350: 400: 450: 500: 560: 630: 710: 800: 900: 1000: 1100: 1300: 1400: 1600: 1800: 2000: 2200: | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Change Focus Mode
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus mode to each of the following values 2: 4: 3: 6: 1: | camera changes the focus mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus mode to each of the following values 2: 4: 3: 6: 1: | camera changes the focus mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus mode to each of the following values 2: 4: 3: 6: 1: | camera changes the focus mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus mode to each of the following values 2: 4: 3: 6: 1: | camera changes the focus mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for focus mode and observe camera | camera changes the focus mode as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for focus mode and observe camera | camera changes the focus mode as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the focus mode setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO
6 |  |  | Change Focus Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu 18 x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the focus mode setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Change Focus Area
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus area to each of the following values in the range 1 to 7 | camera changes the focus area as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus area to each of the following values in the range 1 to 7 | camera changes the focus area as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus area to each of the following values in the range 1 to 7 | camera changes the focus area as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the focus area to each of the following values in the range 1 to 7 | camera changes the focus area as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for focus area and observe camera | camera changes the focus area as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for focus area and observe camera | camera changes the focus area as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the focus area setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO
6 |  |  | Change Focus Area setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu 18 x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the focus area setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Change ShutterSpeed
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the shutter speed to the following values 19660810: 16384010: 13107210: 9830410: 8519690: 6553610: 5242890: 3932170: 3276810: 2621450: 2097162: 1638410: 1310730: 1048586: 851978: 655370: 524298: 393226: 327690: 262154: 65539: 65540: 65541: 65542: 65544: 65546: 65549: 65551: 65556: 65561: 65566: 65576: 65586: 65596: 65616: 65636: 65661: 65696: 65736: 65786: 65856: 65936: 66036: 66176: 66336: 66536: 66786: 67136: 67536: 68036: 68736: 69536: 70536: 71936: 73536: | camera changes the shutter speed as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the shutter speed to the following values 19660810: 16384010: 13107210: 9830410: 8519690: 6553610: 5242890: 3932170: 3276810: 2621450: 2097162: 1638410: 1310730: 1048586: 851978: 655370: 524298: 393226: 327690: 262154: 65539: 65540: 65541: 65542: 65544: 65546: 65549: 65551: 65556: 65561: 65566: 65576: 65586: 65596: 65616: 65636: 65661: 65696: 65736: 65786: 65856: 65936: 66036: 66176: 66336: 66536: 66786: 67136: 67536: 68036: 68736: 69536: 70536: 71936: 73536: | camera changes the shutter speed as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the shutter speed to the following values 19660810: 16384010: 13107210: 9830410: 8519690: 6553610: 5242890: 3932170: 3276810: 2621450: 2097162: 1638410: 1310730: 1048586: 851978: 655370: 524298: 393226: 327690: 262154: 65539: 65540: 65541: 65542: 65544: 65546: 65549: 65551: 65556: 65561: 65566: 65576: 65586: 65596: 65616: 65636: 65661: 65696: 65736: 65786: 65856: 65936: 66036: 66176: 66336: 66536: 66786: 67136: 67536: 68036: 68736: 69536: 70536: 71936: 73536: | camera changes the shutter speed as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the shutter speed to the following values 19660810: 16384010: 13107210: 9830410: 8519690: 6553610: 5242890: 3932170: 3276810: 2621450: 2097162: 1638410: 1310730: 1048586: 851978: 655370: 524298: 393226: 327690: 262154: 65539: 65540: 65541: 65542: 65544: 65546: 65549: 65551: 65556: 65561: 65566: 65576: 65586: 65596: 65616: 65636: 65661: 65696: 65736: 65786: 65856: 65936: 66036: 66176: 66336: 66536: 66786: 67136: 67536: 68036: 68736: 69536: 70536: 71936: 73536: | camera changes the shutter speed as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for shutter speed and observe camera | camera changes the shutter speed as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for shutter speed and observe camera | camera changes the shutter speed as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the shutter speed setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO
6 |  |  | Change Shutter Speed setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu 18 x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the shutter speed setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Change StillCapMode
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the still capture mode to the following values 65543: 1: 65540: 65537: 65538: 196611: 196610: 196609: 524289: 524290: 524293: 524294: 524291: 524292: 393218: 393217: 458754: 458753: 262913 to 262928 327681 to 327696 | camera changes the still capture mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the still capture mode to the following values 65543: 1: 65540: 65537: 65538: 196611: 196610: 196609: 524289: 524290: 524293: 524294: 524291: 524292: 393218: 393217: 458754: 458753: 262913 to 262928 327681 to 327696 | camera changes the still capture mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the still capture mode to the following values 65543: 1: 65540: 65537: 65538: 196611: 196610: 196609: 524289: 524290: 524293: 524294: 524291: 524292: 393218: 393217: 458754: 458753: 262913 to 262928 327681 to 327696 | camera changes the still capture mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the still capture mode to the following values 65543: 1: 65540: 65537: 65538: 196611: 196610: 196609: 524289: 524290: 524293: 524294: 524291: 524292: 393218: 393217: 458754: 458753: 262913 to 262928 327681 to 327696 | camera changes the still capture mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for still capture mode and observe camera | camera changes the still capture mode as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD | modification made but nmot tested
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for still capture mode and observe camera | camera changes the still capture mode as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO
5 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the still capture mode setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO
6 |  |  | Change Still Capture Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to x86 | lights indicate on camera | as described to left | pass | MO | on 64bit ubuntu 18 x86 | 1 | pass |  | MO
[5 empty] | 2 | from Remote Cli Application change the still capture mode setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass |  | MO

## Sony Camera Near Far setting
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Run By
1 |  |  | Change Near/Far Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO | on 64bit manjaro pi | 1 | pass | MO
[5 empty] | 2 | From Remote Cli Application change the still capture mode setting (once as an example) | camera changes to requested setting | as described to left | pass | MO |  | 1 | pass | MO

## Sony Camera Change ExposureProg
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results | Pass/Fail | Run By | Comments | Issue No | re-test C Code |  | Run By
1 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass | intermiitant problem due to usb reset - this has been fixed using pocoLib running the python reset script | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the exposure program mode to the following values 32850: 32848: 32849: 32851: | camera changes the exposure program mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
2 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the exposure program mode to the following values 32850: 32848: 32849: 32851: | camera changes the exposure program mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the exposure program mode to the following values 32850: 32848: 32849: 32851: | camera changes the exposure program mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
3 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO
[5 empty] | 3 | from parameter page change the exposure program mode to the following values 32850: 32848: 32849: 32851: | camera changes the exposure program mode as per the list and reports this data back | as described to left | pass | MO |  | 1 | pass |  | MO
4 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO |  | 1 | pass |  | MO/AD
[5 empty] | 4 | select each option for exposure program mode and observe camera | camera changes the exposure program mode as per the list and reports this data back | no action in camera value sent shows as _XXX | fail | MO | ok with program modified | 1 | fail | with stock program | MO/AD | modification made but nmot tested
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | shows wrongly indicated value | fail | MO | ok with program modified | 1 | fail |  | MO/AD
4 |  |  | Change Exposure Program Mode setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi | lights indicate on camera and pi | as described to left | pass | MO/VKR |  | 2
[5 empty] | 2 | start up QGroundcontrol and connect to the rasberry Pi over serial radio communicating with the flight controller | shows connected | as described to left | pass | MO/VKR |  | 2
[5 empty] | 3 | delete the cached xml file and reconnect esnure you get a new one and the overlay display is showing correctly the menus and descriptions relating to this model of camera | shows overlay with correct pick menus for each of these options EXPOSURE_PROGRAM APERTURE FOCUS_MODE ISO ShutterSpeed WhiteBalance Still Capture Mode FOCUS_AREA | as described to left | pass | MO/VKR |  | 2
[5 empty] | 4 | select each option for exposure program mode and observe camera | camera changes the exposure program mode as per the list and reports this data back | camera changes to desired setting providing it is in the correct mode | pass | MO/VKR |  | 2
[5 empty] | 5 | observe menu indicator shows correct setting | corresponds with value showing on camera screen | inidicates the option as per the camera settings | pass | MO/VKR |  | 2
|  |  | initial start-up value | default | 1 | specify in ini to read ini value | default value is shown as per written in ini file and camera seet accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 2 | specify in ini to read setting from xml | default value is shown as per written in default= of the xml file for this option and camera set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 3 | specify in ini to read last saved values | default value is shown as per written in json of last known values file for this option and camera is set accordingly | as described to left | n/a |  |  |  | pass |  | MO
|  |  |  | default | 4 | specify no recall | camera remains the same all the requests update from the current camera settings and no further action takes place | as described to left | n/a |  |  |  | pass |  | MO

## Boundary Tests
Sprint | User Story for mobile in Jira | User Story for web in Jira | Test Case Name | Test Case Description | Step Name | Step Description | Expected Results | Actual Results(Web) | Pass/Fail | Run By | Comments | Issue No | re-test C Code | Run By
1 |  |  | Check invalid setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 1 | pass
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 1 | pass
[5 empty] | 3 | enter a wrong value and send repeat for each variable | no action and action is deleted no further acton taken | continuous sending of wrong value | fail | MO |  | 1 | not checked
2 |  |  | Check invalid setting | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 2 | pass
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 2 | pass
[5 empty] | 3 | enter a wrong value and send repeat for each variable | no action and action is deleted no further acton taken | as described to left | pass | MO |  | 2 | pass
3 |  |  | Check write protection mode | Sony Alpha 7 Camera | 1 | Power up camera and connect via usb cable to Raspberry Pi ensure camera mode is set to remote operation for this feature | lights indicate on camera and pi | as described to left | pass | MO |  | 2 | pass
[5 empty] | 2 | start up Mission Planner and connect to the rasberry Pi over TCP connection to Port 5670 | shows connected | as described to left | pass | MO |  | 2 | pass
[5 empty] | 3 | enter a valid value but set camera to a write protected mode | no action and action is deleted no further acton taken write protect bit set in word for that feature | as described to left | pass | MO |  | 2 | pass
4 |  |  | ini file values are clamped @ min |  |  | enter value under range in ini file for each setting | ensure minimum value is read | as described to left | pass | MO |  | 2 | pass
|  |  | xml file values are clamped @ min |  |  | enter value under range in xml file for each setting | ensure minimum value is read | as described to left | pass | MO |  | 2 | pass
|  |  | ini file values are clamped at max |  |  | enter value over range in ini file for each setting | ensure maximum value is read | as described to left | pass | MO |  | 2 | pass
|  |  | xml file values are clamped at max |  |  | enter value over range in xml file for each setting | ensure maximum value is read | as described to left | pass | MO |  | 2 | pass